Ustekinumab Implementation Checklist

| Phase 1: Pre-Framework Award |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No. | Task/Action | Person/Team Responsible | In Progress (Date) | Comments/Updates/Decisions |  | Completed (Date) |
| 1 | Identify and appoint a dedicated implementation lead and clinical champion. |  |  |  |  |  |
| 2 | Engage and seek input from across all clinical specialties where the originator is currently used. |  |  |  |  |  |
| 3 | Identify how ustekinumab is funded in your organisation and engage with commissioner (finance, medicines optimisation and contract teams) to support with implementation where required. |  |  |  |  |  |
| 4 | Identify number of patients currently being treated with Stelara and how they are supplied (e.g. homecare, hospital pharmacy, OPD). |  |  |  |  |  |
| 5 | Review and agree which patients will be eligible for the new biosimilar. |  |  |  |  |  |
| 6 | Liaise with homecare providers to understand their processes for managing the switch (whether you plan to stay with current provider or move providers). |  |  |  |  |  |
| 7 | Consider how patients will be informed and/or consented. |  |  |  |  |  |
| 8 | Prepare patient information and agree how this will be distributed. |  |  |  |  |  |
| 9 | Manage stock of Stelara held in hospital pharmacy or in outpatient providers. |  |  |  |  |  |
| 10 | Review SPS guidance and available information on biosimilars being launched |  |  |  |  |  |
| Phase 2: Post-Framework Award – Pre-Framework Start date |  |  |  |  |  |  |
| No. | Task/Action | Person/Team Responsible | In Progress (Date) | Comments/Updates/Decisions | Completed (Date) |  |
| 1 | Review Framework award documentation to understand prices and presentations offered by each supplier. |  |  |  |  |  |
| 2a | Liaise with clinical teams to agree on chosen biosimilar(s) (consider cost, formulation, presentation, QA assessment, supply route) |  |  |  |  |  |
| 2b | Agree whether switching will happen at the same time for all indications or specific indications (excluding UC). |  |  |  |  |  |
| 3 | For homecare patients, consider whether bundled or unbundled services will be most appropriate and cost effective. |  |  |  |  |  |
| 4 | Contact supplier of chosen biosimilar(s) to notify them of patient numbers and confirm they have capacity (and can supply from anticipated switch date). |  |  |  |  |  |
| 5a | Inform chosen homecare provider of decision and agree mechanism and timeline for the switch ensuring minimal delay based on delivery frequencies (request exit data if moving providers). |  |  |  |  |  |
| 5b | Ensure service level agreement with homecare provider is in place. |  |  |  |  |  |
| 6 | Engage with patients ahead of the switch by informing them of potential changes to their medication and/or home care services to maintain patient trust. Multiple channels of communication should be used, including face to face discussions regarding changes, letters, leaflets, video training produced by the supplier. |  |  |  |  |  |
| 7a | Ensure biosimilar is available on the local formularies via local governance processes and committees (such as Medicines Management Committees or equivalent). |  |  |  |  |  |
| 7b | Build drug files on pharmacy systems (including for homecare and OPDs if required) |  |  |  |  |  |
| 8 | Ensure stock and drug files for Stelara are managed to run down existing stock (consider what stock may be needed for ulcerative colitis patients) |  |  |  |  |  |
| 9 | Communicate appropriately with all stakeholders (clinical teams, pharmacy teams, OPDs etc) so that they aware of the change in product and commencement date. |  |  |  |  |  |
| 10 | Inform Regional Pharmacy Procurement Specialists of your chosen biosimilar(s) and switch timelines. |  |  |  |  |  |

| Phase 3: Post-Framework Start Date |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| No. | Task/Action | Person/Team Responsible | In Progress (Date) | Comments/Updates/Decisions | Completed (Date) |
| 1 | Order stock of biosimilar presentations into hospital pharmacy or outpatient providers if required. |  |  |  |  |
| 2 | Manage drug files on pharmacy systems to reduce/remove minimum reorder levels if appropriate (some stock of Stelara presentations may be needed for ulcerative colitis patients) |  |  |  |  |
| 3 | Work with homecare providers and clinical teams to progress biosimilar switch to agreed mechanism and timelines |  |  |  |  |
| 4 | Monitor patients for adverse events and ensure regular follow up |  |  |  |  |
| 5 | Report to clinicians, finance, regional pharmacy procurement specialists about the ongoing switch progress |  |  |  |  |