## Summary
Framework Implementation Trust Level Checklist
This document describes the activities for consideration/completion at a trust level, to implement MPSC Transition frameworks.
The actvities in the PostAward and GoLive tabs will also be relevant to other established MPSC frameworks.
Instructions: enter the information required on the Pre Award, Post Award or Go Live tabs. The Summary table below will auto populate.
Medicine name:
Activity | Completed | Deadline
Pre Award Early Engagement
Main areas of use identified | 0 | 0
Clinical appropriateness considered | 0 | 0
Demand patterns determined | 0 | 0
Stockholding assessed | 0 | 0
Pre Award 3 months
Requirement for patient communications considered | 0 | 0
Draft switching plan considered | 0 | 0
Clinical and operational leads engaged | 0 | 0
Commercial providers engaged | 0 | 0
Slow moving stock reviewed | 0 | 0
Commercial OPD engaged | 0 | 0
Post Award
Opportunities reviewed, action plan developed | 0 | 0
Plan for pharmacy aseptic/manufacturing changes in place | 0 | 0
Framework uploaded to pharmacy system | 0 | 0
Stock depletion plan in place | 0 | 0
Risk assessments completed | 0 | 0
New product catalogue entries set up | 0 | 0
Transition plan for discontinued products in place | 0 | 0
Anticpated change in demand communicated | 0 | 0
New suppliers set up | 0 | 0
End user communications issued | 0 | 0
IV monographs available | 0 | 0
E-prescribing systems prepared | 0 | 0
PowerGate/Medecator systems prepared | 0 | 0
Slow moving stock reviewed | 0 | 0
Homecare switching plan agreed | 0 | 0
Homecare exit data requested | 0 | 0
Electronic homecare prescription pathways updated. | 0 | 0
Outsourced providers informed | 0 | 0
Go Live
Stock holding parameters updated | 0 | 0
EAN/GTIN codes updated | 0 | 0
Replaced products discontinued | 0 | 0
Stock lists amended | 0 | 0
System in place for homecare order price changes | 0 | 0
Changes to original awards actioned | 0 | 0
Progress monitoring in place | 0 | 0

## PreAward
Pre Award
Medicine name:
Activity / Timeline | Person Responsible | Deadline | Completed | Comments
6 months - early engagement
Identify main areas of use/activity/supply route, e.g. inpatients, outpatients, homecare, aseptics, speciality
Consider clinical appropriateness - will Formulary approval be required?
Determine demand patterns and stockholding algorithms (e.g. prescription cycles and lengths - homecare, hospital, FP10s, influencing stockholding quantities and ordering frequencies)
Understand stockholding in all locations e.g. hospital, third-party outpatients, aseptics
3 months
Consider if patient communications will be required
Consider drafting switching plan (assess stockholding, demand patterns, prescription cycles/lengths, IT systems used)
Engage with clinical and operational leads
Engage with commercial homecare providers to understand switching requirements. Explore requirements for bulk switching patients, patient-by-patient, approval process for documentation e.g. registration, prescription templates, SLAs.
Consider re-distribution of surplus, slow-moving stock to high-turnover areas.
Engagement with commerical OPD provider to advise of potential upcoming changes and request support with managing stock.

## PostAward
Post Award - On receipt of framework award detail from MPSC
There is considerable variation between trusts for updating frameworks depending on the systems they use (e.g. JAC/Emis, PowerGate/Medecator, framework upload functionality, e-prescribing etc.).
The following list details tasks applicable to most trusts that should be reflected in local trust standard operating procedures.
Medicine name:
Activity / Timeline | Person Responsible | Deadline | Completed | Comments
On receipt of award detail, up to six weeks before framework start
Review opportunities for savings/cost-avoidance. Start developing CIP proposal/action plan. Instigate any Formulary documentation and necessary actions.
Identify products used locally in aseptics or production (e.g. IV chemo or tablets for over-labelling) for validation and documentation (e.g. production worksheets) review/update.
Load framework detail to each pharmacy system location (e.g. Stores, Homecare, Outsourced Outpatients, multiple hospital sites): manually for each line on each location or using automated framework upload functionality.
Manage ordering systems so existing stock is depleted as soon as possible after framework go live and the new contract product is ordered.
Complete local product risk assessments; plan any risk mitigation actions for products identified in any QA Packaging & Labelling Assessment Reports.
Create new products on systems (including System Support requests for new products or pack sizes, dm+d codes etc.)
For products to be replaced (e.g. new pack sizes or change to a different product) develop plan to transition to new and exhaust old products.
If usage is anticipated to increase/decrease due to a change in clinical practice or product switching, advise A/RPPS and engage with suppliers to confirm new volumes can be supported. Action any onboarding requirements.
Create new suppliers on systems (to include supplier approval/validation).
Prepare/issue any communications necessary for users/patients/other stakeholders.
Ensure IV monographs etc. are available.
Prepare e-prescribing system for any necessary changes e.g. 'debranding' prescriptions .
Upload MPSC expiry date matching file to PowerGate; resolve exceptions / Map frameworks on Medecator.
Consider re-distributing slow-moving stock to high-turnover areas if necessary.
Liase with any homecare providers if switching to agree mechanism and timeline.
Request exit data from homecare providers if required.
Update electronic pathways for Esign homecare prescriptions if necessary.
Advise any outsourced providers of new prices e.g. homecare or outpatients (~4 weeks’ notice required).

## GoLive
Go Live - from Day 1 of framework
Medicine name:
Activity / Timeline | Person Responsible | Deadline | Completed | Comments
Framework start
Update stock holding parameters on pharmacy system
Update EAN/GTIN codes on pharmacy / e-commerce systems
Discontinue any products replaced by new products (e.g. new pack sizes), once stock exhausted.
Amend clinical area stock lists (as necessary).
System in place with Pharmacy/Finance to adjust homecare pricing for orders placed prior to framework start.
Action any changes to original awards.
Monitor implementation progress including homecare/OPD until completion.